## Summary_known_issue
S/N | core-v-verif ticket# | Known issue | Category | Status | Random/Custom | Example failing test(s) | Example error message(s)
1 |  | Instruction number in HWLOOP body exceeding maximum number of instruction when using immediate version of HWLOOP instructions (cv.counti, cv.setupi). This issue seen rarely, maybe 1 out of 2~3 regressions. Too risky to fix it now as it might affect other tests. | Test generation corner case | Open (no fix) | Random | corev_directed_for_hwloop_covg_test | test_program/corev_directed_for_hwloop_covg_test_550986902.S:826:(.text+0xbb4): relocation truncated to fit: R_RISCV_CVPCREL_UI12 against `hwloop1_end_stream1_id0'
2 |  | Mismatch between RTL and Imperas model on first debug request | Imperas Model | Open (no fix) | Random | corev_rand_pulp_instr_test | # Info (IDV) Instruction executed prior to mismatch '0x80(_start+0): 0800006f j 100' # Error (IDV) PC mismatch (HartId:0, PC:0x00000100 _start_main+0): # Error (IDV) Mismatch 0> # Error (IDV) . dut:0x1a110800 debug_rom+0 # Error (IDV) . ref:0x00000100 _start_main+0 # Error (IDV) Insn. bit pattern mismatch (HartId:0, PC:0x00000100 _start_main+0):