## README
Copyright 2020, 2023, 2024 by the OpenHW Group
Licensed under the Solderpad Hardware License, Version 2.1
Purpose of this Document
This document is the Checklist for the TRL-5 Release for OpenHW Group "CORE-V" RTL IP.
CORE-V
Most, but not necessarily all, OpenHW Group RTL IP is an implementation of a RISC-V compliant processor core. These cores are branded as the CORE-V family. Many of the items in this Checklist will be specific to this type of IP.
RTL IP
For the purposes of this document, RTL IP shall mean designs and associated collateral that can be use to realize a functional design in either an FPGA, ASIC or both. The RTL IP is captured as synthesizable SystemVerilog.
What Does “TRL-5” Mean?
RTL that meets the TRL-5 criteria is complete, functionally correct, validated against a specific software toolchain and ready to be used in a commercial-grade product. The Specification, Design and Verification are complete and self-consistent. It has been shown to match the design intent as captured in the specification by means of either dynamic or static verification methods (or both).
Deliverables: OpenHW provides the following at TRL-5:
- A complete User Manual including implementation guidelines
- RTL source code (licensed under Solderpad 2.0)
- Verification Plans and Reports
- Verification Environment source code
- Software compliance report
A note out Physical Implementations
IP that achieves the TRL-5 criteria is subject to a set of RTL design rules and lint checks. It may or may not have been synthesized and implemented into a physical gate model.

## Documentation
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | Exceptions/Waivers
Publication | User Manual | Tagged version of source available in cv32e40p | pascal.gouedo@dolphin.fr | 2024-07-11 | cv32e40p_v1.8.3
|  | Formally released static version attributed to programs tag | pascal.gouedo@dolphin.fr | 2024-07-11
|  | No open or non-waived issues assigned to tagged release | pascal.gouedo@dolphin.fr | 2024-07-05
| Errata | List of waived programs issues related to tagged release | pascal.gouedo@dolphin.fr | 2024-07-05 | None
User Manual Content | CORE Integration | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
Completed RISC-V ISA Compliance Review
| Micro-architecture of each major design unit | Chapter(s) reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
| ISA of CORE-specific instruction extensions | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
Completed RISC-V ISA Compliance Review
| Control and Status Registers | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
Completed RISC-V ISA Compliance Review
| Performance Counters | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
Completed RISC-V ISA Compliance Review
| Exceptions and Interrupts | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
Completed RISC-V ISA Compliance Review
| Debug support | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
|  | Completed RISC-V ISA Compliance Review |  | 2024-07-05
| Trigger support | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
Completed RISC-V ISA Compliance Review
| Tracer support | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05
| Verification Highligths |  | pascal.gouedo@dolphin.fr | 2024-07-05
| Synthesis guidelines | Chapter reviewed and signed-off as a complete. | pascal.gouedo@dolphin.fr | 2024-07-05

## IP
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | Exceptions/Waivers
IP Review | IP review of source code in RTL design repo | Eclipse “CQ” audit complete
| IP review of source code in verification repo | Eclipse “CQ” audit complete
| IP audit on User Manual | OpenHW Staff audit compete

## RTL Design
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | Exceptions/Waivers
Configuration | Version clearly identified | The version at this release is clearly identified in GitHub and in the release review document. | pascal.gouedo@dolphin.fr | 2024-07-09 | Last RTL updates in cv32e40p_v1.8.0 tag Final tag is cv32e40p_v1.8.3
Coding rules | Module and File names | No two modules in the design have the same name. Each module name shall be prefixed with the project name (e.g. cv32e40p_<module>) Each module name shall match the file name using the system verilog suffix ".sv" (e.g. cv32e40p_controller module located in cv32e40p_controller.sv file) Each system verilog file shall contain only one module definition | pascal.gouedo@dolphin.fr | 2024-05-15
| Implementation HDL | The design does not mix HDLs. | pascal.gouedo@dolphin.fr | 2024-05-15
| Low technology dependence | In IP designs, technology-specific blocks (mainly RAM cells) are accessible and easily replaced by blocks targetting other ASIC or FPGA technologies. | pascal.gouedo@dolphin.fr | 2024-05-15
| No use of ifdef, ifndef, defines, includes | No ifdef, ifndef or defines used anywhere in RTL No files included anywhere in RTL | pascal.gouedo@dolphin.fr | 2024-05-15 | Except for assertions, which shall be within a define using the project name (e.g. <PROJECT_NAME>_ASSERT_ON) includes only in vendorized CVFPU 0.8.1 and (FPnew) and PULP_PLATFORM_COMMON_CELLS
| No unfinished code | No comments in code alluding to potential fixes or changes. Comments include "todo", "tbd", "fixme" | pascal.gouedo@dolphin.fr | 2024-05-15
| No open non-waived RTL bugs in github | No open non-waived issues with both label Component:RTL and Type:Bug | pascal.gouedo@dolphin.fr | 2024-06-05 | Waiving can be done by applying the WAIVED:<PROJECT_NAME>. Issues labeled with a non-applicable parameter option are waived as well in case the release configuration applies to a different parameter configuration
| No dependency on external repositories for design | No dependency on external repositories for design | pascal.gouedo@dolphin.fr | 2024-05-15 | CVFPU v0.8.1 vendorized in rtl directory
Design rules | Clock domain crossing | Synchronizers shall be implemented with a component module (similar to clock gate) in order for implementation to replace with 2 or 3 flip-flop synchronizer based on technology and MTBF requirements | pascal.gouedo@dolphin.fr | 2024-05-15 | Only 1 clock domain
| Asynchronous inputs | Asynchronous inputs have an adequate synchronizer(s). | pascal.gouedo@dolphin.fr | 2024-05-15 | No synchronizer.
| Synchronous design | Fully synchronous design | pascal.gouedo@dolphin.fr | 2024-05-15 | Other design styles clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Synchronous design | No delay line (based on propagation time) | pascal.gouedo@dolphin.fr | 2024-05-15
| Synchronous design | No combinational loops. Tool used to check it. | pascal.gouedo@dolphin.fr |  | Tool name and version in Tools tab
| Multicycle path | No multicycle path. Tool used to check it. | pascal.gouedo@dolphin.fr | 2024-05-15 | If Multicycles necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines. Tool name and version in Tools tab
| Clock edges | Only one active clock edge in the design | pascal.gouedo@dolphin.fr | 2024-05-15 | Other clock schemes necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Gating clock | Gated clocks necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines. | pascal.gouedo@dolphin.fr | 2024-05-15
| No latch | Latches may be implemented for large memory elements (such as register files) using a parameter to select between register vs latched design. | pascal.gouedo@dolphin.fr | 2024-05-15
| Reset signal | Only one reset signal in the design | pascal.gouedo@dolphin.fr | 2024-05-15 | Other design styles necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Reset fanout | Same type of reset in the whole design (synchronous/asynchronous, active high/low) | pascal.gouedo@dolphin.fr | 2024-05-15
| FSM reset | FSM state register has a reset | pascal.gouedo@dolphin.fr | 2024-05-15
| No tri-state | No internal tri-state buffers | pascal.gouedo@dolphin.fr | 2024-05-15 | Does not apply to I/O pads.
| Files formatting | verible | pascal.gouedo@dolphin.fr | 2024-05-15 | Version in Tools tab
Synthesizable IP | Linting | Tool used to check it. It reports no error and all outstanding warnings can be waived. | pascal.gouedo@dolphin.fr | 2024-05-15 | Tool name and version in Tools tab
Open-source | Third-party audit | Eclipse “CQ” audit complete
| No closed-source | All RTL code in the design is open-source. It includes the appropriate licence notices. | pascal.gouedo@dolphin.fr | 2024-05-15
| OpenHW design licence | OpenHW Group RTL source code is under the Solderpad 2.0 licence | pascal.gouedo@dolphin.fr | 2024-05-15
| Third-party IP licence | Third party IP licence terms do not contaminate other designs in the modules and do not prevent to use the design in closed-source projects (e.g. GPL IP cannot be integrated in OpenHW projects). | pascal.gouedo@dolphin.fr | 2024-06-21 | No third-party IP.
| No export restrictions | Contributions do not include controlled software or technology or other information that is subject to export control laws and regulations in any applicable jurisdictions, including but not limited to U.S. Export Administration Regulations (15 CFR Chapter VII, Subchapter C, Parts 730-744, EAR). [Excerpt from OpenHW Group Membership Agreement] OpenHW members are bound to this agreement; the use of external IP is not. | pascal.gouedo@dolphin.fr | 2024-06-21 | Nothing subject to export control.

## Simulation Verification
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | Exceptions/Waivers | Comments
Verification Planning | Top-level Verification Plan | Top-level plan is complete | beenee.lim@dolphin.fr | 2024-05-15 | None allowed
| Per-functional Category Verification Plan | Completed, reviewed and up-issued per review | beenee.lim@dolphin.fr | 2024-05-15 | Captured as core-v-verif issues | None
| Testbench Cross-reference | Each item in Vplan cross-ref’ed to testcase and/or coverage | beenee.lim@dolphin.fr | 2024-05-31 | Captured as core-v-verif issues | None
Code Coverage | 100% Block/Statement Coverage | All Blocks covered |  |  | None allowed exception for those related to fixed parameters | >99%. Controller remaining.
| 100% Branch Coverage | All branches covered |  |  | Waivers captured as core-v-verif issues | >99%. Controller remaining.
| 100% Conditional Coverage | All conditions covered |  |  | Waivers captured as core-v-verif issues | >99%. Controller remaining.
Functional Coverage | All cover-points attributed to a Vplan item | Human review | beenee.lim@dolphin.fr | 2024-05-31 | Captured as core-v-verif issues
| All cover properties attributed to a Vplan item | Human review | beenee.lim@dolphin.fr | 2024-05-31 | Captured as core-v-verif issues
| Cover-point coverage | 100% | beenee.lim@dolphin.fr | 2024-05-22 | Captured as core-v-verif issues | 100%
| Cover-property coverage | 100% | beenee.lim@dolphin.fr | 2024-05-15 | Captured as core-v-verif issues | 100%
Regression | Compliance Test Suite | All RISC-V Compliance tests run and passing | beenee.lim@dolphin.fr | 2024-05-15 | None allowed
| CORE-specific Test Suite | All tests run and passing | xavier.aubert@dolphin.fr | 2024-07-05 | Captured as core-v-verif issues | >99.9%
Final Report | Verification Plans |  | pascal.gouedo@dolphin.fr | 2024-06-21
| RISC-V Architecture tests reports |  | pascal.gouedo@dolphin.fr | 2024-06-21 | One report line for each configuration | Done on RTL v1.8.3 for final report
| Regression Results |  | pascal.gouedo@dolphin.fr | 2024-06-21 |  | Done on RTL v1.8.3 for final report
| Coverage Results |  | pascal.gouedo@dolphin.fr | 2024-06-21 |  | Done on RTL v1.8.3 for final report

## Formal Verification
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | Exceptions/Waivers
Verification Planning | RISC-V ISA Formal Verification methodology | https://github.com/openhwgroup/core-v-verif/blob/cv32e40p_v1.8.3/cv32e40p/docs/VerifPlans/RISC-V_ISA_Formal/CV32E40Pv2_RISCV_vPlan_v1.1.pdf | pascal.gouedo@dolphin.fr | 2024-07-05
| RV32IMCXpulp Vplan | https://github.com/openhwgroup/core-v-verif/blob/cv32e40p_v1.8.3/cv32e40p/docs/VerifPlans/RISC-V_ISA_Formal/CV32E40Pv2_Formal_VerificationPlans.xlsx | pascal.gouedo@dolphin.fr | 2024-07-05
Assertions | Tool generator or humanly written | Generated by a tool | pascal.gouedo@dolphin.fr | 2024-07-05
| Tool name and version | Siemens Questa Processor 2024.2 | pascal.gouedo@dolphin.fr | 2024-07-05
| Tool setup and scripts | https://github.com/openhwgroup/cv32e40p/tree/cv32e40p_v1.8.3/scripts/riscv_isa_formal | pascal.gouedo@dolphin.fr | 2024-07-05
| Assertions file format and location | Encrypted tool generated SystemVerilog file | pascal.gouedo@dolphin.fr | 2024-07-05
Regression | Formal Testbench | All assertions hold unbounded with reachable witnesses | pascal.gouedo@dolphin.fr | 2024-07-05 | CFG_P and CFG_P_F0 100% covered
Final Report | Verification Plans | https://github.com/openhwgroup/core-v-verif/blob/cv32e40p_v1.8.3/cv32e40p/docs/VerifPlans/RISC-V_ISA_Formal/CV32E40Pv2_Formal_VerificationPlans.xlsx | pascal.gouedo@dolphin.fr | 2024-07-05
| Regression Results | https://github.com/openhwgroup/programs/blob/cv32e40p_v1.8.3/Project-Descriptions-and-Plans/CV32E40Pv2/Milestone-data/RTL_v1.8.3/Reports/RISC-V_ISA_Formal/Property_Status-v1_8_3.xlsx | pascal.gouedo@dolphin.fr | 2024-07-05
| Coverage Results | https://github.com/openhwgroup/programs/blob/cv32e40p_v1.8.3/Project-Descriptions-and-Plans/CV32E40Pv2/Milestone-data/RTL_v1.8.3/Reports/RISC-V_ISA_Formal/Property_Status-v1_8_3.xlsx | pascal.gouedo@dolphin.fr | 2024-07-05

## Software Requirements
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | Exceptions/Waivers | OpenHW Req'mt? | Discussion/Comments
GCC Toolchain | GCC sources | Provide open-source (not corporate) URL to Repository *and* tag | jeremy.bennett@embecosm.com | 2024-05-30 |  | Yes (unless LLVM is used) | GCC source: https://github.com/openhwgroup/corev-gcc Binutils/GDB source:https://github.com/openhwgroup/corev-binutils-gdb Newlib source: http://sourceware.org/git/newlib-cygwin.git GCC tag: cv32e40pv2-release Binutils/GDB tag: cv32e40pv2-release Newlib tag: newlib-4.4.0 Release notes: https://docs.google.com/document/d/1PfOGXvmB_Kpx_lPL-m4I8Yl_PZeyjsIsDyunuOhGwA8 Pre-built binaries: https://www.embecosm.com/resources/tool-chain-downloads/#corev
| Binutils sources | Provide open-source (not corporate) URL to Repository *and* tag | jeremy.bennett@embecosm.com | 2024-05-30 |  | Yes (unless LLVM is used)
| C Library sources (e.g. glibc or newlib) | Provide open-source (not corporate) URL to Repository *and* tag | jeremy.bennett@embecosm.com | 2024-05-30 |  | Yes (unless LLVM is used)
| Release Notes | Included with Tagged Release | jeremy.bennett@embecosm.com | 2024-05-30 |  | Yes (unless LLVM is used)
| Pre-built binaries | Provide URL | jeremy.bennett@embecosm.com | 2024-05-30 |  | No
LLVM Toolchain | LLVM sources | Provide open-source (not corporate) URL to Repository *and* tag |  |  | N/A | No (unless GCC not used)
| Binutils sources | Provide open-source (not corporate) URL to Repository *and* tag |  |  | N/A | No (unless GCC not used)
| C Library sources (e.g. glibc or newlib) | Provide open-source (not corporate) URL to Repository *and* tag |  |  | N/A | No (unless GCC not used)
| Release Notes | Included with Tagged Release |  |  | N/A | No (unless GCC not used)
| Pre-built binaries | Provide URL |  |  | N/A | No
Toolchain + Core Regression Testing | Toolchain | Indicate which toolchain (from above) was used. |  |  |  | Regression testing of the toolchain on the core is required if the core supports a non-standard ISA. Srongly recommended in all case anyway. | Regression testing may involve multiple toolchains and multiple platforms. In this case, add rows to this check for each Toolchain/Platform/Testsuite combination used.
| Regression Platform: Verilator model, FPGA board, HW Emulator,... | Regression platform stable/working. Must be an implementation of the platform integrating the CORE-V core (i.e. not QEMU, Spike, etc.) |  |  |  |  | Instructions for re-creating the Regression Platform must be included.
| GCC regression: C and C++ | Published regression results |  |  |  |  | Waive if GCC not used.
| LLVM lit tests | Published regression results |  |  |  |  | Waive if LLVM not used.
| LLVM using gcc C and C++ tests (excluding gcc-specific tests) | Published regression results
| LLVM testsuite (Application Cores only) | Published regression results
| Regression Report | Summary of results to be recorded in Release Notes (see Toolchain)
Benchmarks | Embench (i.e. iot, dsp,...) and version | Sign-off for any/all Benchmarks are: 1. URL/tag of the benchmark used 2. Indication that the benchmark ran successfully 3. Results obtained 4. Benchmark-specific report (as required by the benchmark itself) | jeremy.bennett@embecosm.com | 2024-04-05 |  | No | Embench 1.0 succesful using https://github.com/jeremybennett/embench-iot/tree/dolphin-fpga Size score: 0.98, Speed score: 0.96
| Coremark |  |  |  |  | No | Location of specific Coremark regression must be provided.
| SPEC CPU |  |  |  |  | No | Application cores only.
| Others... |  |  |  |  | No | Location of your "other" benchmark must be provided.
Application Code | Project specific (i.e. Linux, RTOS,...) | Published results |  |  |  | No | Location of the application code library must be provided.

## Physical Implementation
Category | Item | Sign-off Criteria | Signed-off By | Sign-off Date | OpenHW Req'mt? | Comments
Synthesis | Tool |  | Email address of Contributor with sign-off authority |  | No | Tool name and version in Tools tab
| Technology & Operating Conditions |  |  |  | No | No foundry name, just technology node (i.e. 90HP, 40LP, 22FDSOI,...)
| Constraints (clock margins,...) |  |  |  | No
No
No
Back-end | Tool |  |  |  | No | Tool name and version in Tools tab
| Clock Tree Synthesis constraints? |  |  |  | No
No
No
No
Power analysis | Tool |  |  |  | No | Tool name and version in Tools tab
| Input stimulis? |  |  |  | No
No
Result 1 | RTL Configuration (Parameters,...) |  |  |  | No
| Area, Max Frequency, Logic Level number,... |  |  |  | No
| Power Consumption/Energy for X benchmark |  |  |  | No
| Power Consumption/Energy for Y benchmark |  |  |  | No
No
No
Result 2 | RTL Configuration (Parameters,...) |  |  |  | No
| Area, Max Frequency, Logic Level number,... |  |  |  | No
| Power Consumption/Energy for X benchmark |  |  |  | No
| Power Consumption/Energy for Y benchmark |  |  |  | No
No
No

## Tools list & versions
| Provider | Tool | Version | Operating system | Comments
RTL file formatter | ChipsAlliance | verible | v0.0-1149-g7eae750 | CentOS 7
Lint tool | Siemens | QuestaSim QuestaFormal | 2022.4 2022.4 | CentOS 7 CentOS 7
Simulation tool | Siemens | QuestaSim | 2023.2_1 | CentOS 7
RISC-V ISA Formal Proof | Siemens | Questa Processor | 2024.2 | CentOS 7
Formal Tool | Siemens | QuestaSim QuestaFormal | 2022.4 2022.4 | CentOS 7 CentOS 7
Reference Model | Synopsys | ImperasDV | eng.20240530.0 | CentOS 7
Software Toolchain | Embecosm | GNU GCC & binutils | corev-openhw-gcc-centos7-20240530 | CentOS 7
Logic Equivalence | Cadence Synopsys | Conformal Formality | 21.20-s200 R-2020.09 | CentOS 7 CentOS 7
Synthesis tool | Synopsys | Design Compiler | U-2022.12-SP7 | CentOS 7
Back-End tool | Cadence | Innovus | v21.11-s130_1 | CentOS 7
Parasitics Extraction | Synopsys | StarRC | S-2021.06 | CentOS 7
Static Timing analysis | Synopsys | Primetime | Q-2019.12-SP2 | CentOS 7
Power Analysis tool | Synopsys | Primetime | Q-2019.12-SP2 | CentOS 7