## Summary_known_issue
S/N | core-v-verif ticket# | Known issue | Category | Status | Random/Custom | Example failing test(s) | Example error message(s) | Comment
1 | 2501 | Mismatch between RTL and Imperas model on first debug request | Reference Model | Open (no fix) | Random | corev_rand_pulp_instr_test | # Info (IDV) Instruction executed prior to mismatch '0x80(_start+0): 0800006f j 100' # Error (IDV) PC mismatch (HartId:0, PC:0x00000100 _start_main+0): # Error (IDV) Mismatch 0> # Error (IDV) . dut:0x1a110800 debug_rom+0 # Error (IDV) . ref:0x00000100 _start_main+0 # Error (IDV) Insn. bit pattern mismatch (HartId:0, PC:0x00000100 _start_main+0): | From Synopsys: It looks as though the haltreq is getting consumed by some additional processing that is done at time zero; actually on the first instruction retirement. Analysis on-going on Synopsys R&D side.
2 | 2497 | Due to randomness of external events vs code generation, some tests can run longer than expected and can timeout (e.g. CPU spending much more time in idle, too many illegal/interrupt causing much more handlers calls (and therefore much more instructions executed, ...) | Test generation corner case | Open (no fix) | Random | corev_rand_wfi_mem_stress_test | # UVM_FATAL @ 50000000.000 ns : uvm_phase.svh(1506) reporter [PH_TIMEOUT] Explicit timeout of 50000000.000 ns hit, indicating a probable testbench issue | Solved by increasing time-out value for the few failing tests
3 | 2502 | In very rare cases, the corev-dv instruction generator is producing a code that doesn't prevent context save to be stored at program memory location, and this risk is significantly higher when those context switching events are nested (nested interrupt, ...). | Test generation corner case | Open (no fix) | Random | corev_rand_interrupt_nested | # 1092476.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # Warning (RISCV_UDEC) CPU 'refRoot/cpu' 0x0001f4d2 00000077 undef: Undecoded instruction # 1093907.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1093910.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1093913.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1093916.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1093919.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1093922.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # Warning (RISCV_UDEC) CPU 'refRoot/cpu' 0x0001f4d2 00000077 undef: Undecoded instruction # 1095314.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1095317.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # 1095320.000 ns: Illegal instruction (core 0) at PC 0x0001f4d2: # Warning (RISCV_UDEC) CPU 'refRoot/cpu' 0x0001f4d2 00000077 undef: Undecoded instruction | A lot of corner cases have been corrected, but during the last regression this very last one appeared, and did not have the time to solve it.
4 | N/A | Few weeks before ending CV32E40Pv2 on Dolphin's side, cv32e40pv2_interrupt_debug.yaml regression lasted 4-5x times longer that before. At this point we were not sure if the culprit was recent modifications or infrastructure issues inside our company (compute-farm, licence server, our Jenkins environment, etc.). | Test performance | Open (no fix) | All | regression: cv32e40pv2_interrupt_debug | RegressionCompleted: Regression finished at Wed May 29 21:59:52 2024 VRM total elapsed time: 656m:49s ( few weeks later ... ) RegressionCompleted: Regression finished at Thu Jun 27 16:04:33 2024 VRM total elapsed time: 4340m:54s | As it may not be a core-v-verif issue, we did not enter this as a separate issue.