## Summary
“Found By” Classification | Count | Note
Simulation | 15 | Sum of sub-classifications below
Inspection | 15 | Confidence in this classification is low – few issues explicitly stated that they were found by inspection
Formal Verification | 18
Lint | 2
Unknown | 0
Simulation sub-classifications | Count | Note
Directed, self checking test | 7 | Many directed tests supplied by Designers and a couple by the Open Source Community at large
Step & Compare | 0
corev-dv | 8 | Simulation with corev-dv also uses step & compare
Type | Count | Note
RTL functional | 46
RTL coding style | 6 | Linter issues, removing TODOs, removing `ifdefs, etc.
Non-RTL functional | 0
Unreproducible | 0
Invalid | 3

## review
Useful issues filtering command for easiest analysis
| All questions after v1 |  | 4 | Filter: | is:issue label:Component:RTL label:Type:Question -label:WAIVED:CV32E40P -closed:<=2020-12-31 sort:created-asc
| All enhancements after v1 |  | 11 |  | is:issue label:Component:RTL label:Type:Enhancement,Type:Task -label:WAIVED:CV32E40P -closed:<=2020-12-31 sort:created-asc
| All bugs after v1 |  | 40 |  | is:issue label:Component:RTL label:Type:Bug -label:WAIVED:CV32E40P -closed:<=2020-12-31 sort:created-asc
| All issues after v1 |  | 55 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P -closed:<=2020-12-31 sort:created-asc
| All issues after v1 closed before v2 |  | 5 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P -closed:<=2020-12-31 -closed:>=2022-01-01 is:closed sort:created-asc
| Remaining v2 issues |  | 50 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P -closed:<=2022-01-01 sort:created-asc
| Issue created during v1 concerning v2 |  | 11 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P created:<2022-01-01 closed:>2022-01-01 sort:created-asc
| Issue created during v2 |  | 35 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P created:>2022-01-01 sort:created-asc
| Issue closed during v2 |  | 46 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P closed:>2022-01-01 sort:created-asc
| Issues still open |  | 0 |  | is:issue label:Component:RTL label:Type:Bug,Type:Enhancement,Type:Question,Type:Task -label:WAIVED:CV32E40P is:open sort:created-asc
| Issues found by Formal Verification |  | 18
| Issues found by Verification by simulation |  | 20
| Issues found by Lint/Coding Style |  | 4
|  |  | Resolved | 45
|  |  | Not a bug | 7 |  |  |  | Doc | Formal | Simulation | Lint/Coding style
|  |  | Waived | 3
|  |  | Open | 0 |  |  |  | 8 | 18 | 20 | 4
Issue # | Title | Type | Creation Date | Resolution Date | Last update | Found By | Notes
169 | Illegal Instruction Exception not Raised - Dynamic Rounding Mode | RTL functional | Sep 27, 2019 | Resolved Apr 28, 2023 |  | Formal Verification | issue from v1 that was resolved during v2 verification Resolved with PR #801 |  | X
170 | Illegal Instruction Exception not Raised - FS Field | RTL functional | Sep 27, 2019 | Resolved Jun 23, 2023 |  | Formal Verification | issue from v1 that was resolved during v2 verification Resolved with PR #801 |  | X
174 | Incorrect F Extension Result Calculation - Dynamic Rounding Mode | RTL functional | Sep 30, 2019 | Resolved Apr 28, 2023 |  | Formal Verification | issue from v1 that was resolved during v2 verification Resolved with PR #801 |  | X
197 | Prefetch buffer issue when IRQ arrived on last instruction of the HW loop body | RTL functional | Nov 13, 2019 | Not a bug Aug 4, 2023 |  | Simulation (directed) | issue from v1 that was resolved during v2 verification New hwloop constraints in v2 "solved" this issue
252 | Align the code to the lowRISC style-guide | RTL coding style | Mar 5, 2020 | Waived June 4, 2024 |  | Inspection | Opened during v1 and not closed at the end of the project Just a better good-looking RTL coding style
308 | Code not running with fpnew in verilator | RTL functional | Apr 17, 2020 | Not a bug Jul 24, 2020 |  | Simulation (directed) | issue from v1 that was resolved during v2 verification author of the issue did not update the status during the last three years, it has been marked as resolved.
452 | Some of the Xpulp instructions use opcodes that are either reserved opcodes or standard opcodes | RTL functional | Aug 19, 2020 | Resolved Apr 18, 2023 |  | Inspection | Issue opened in v1, one of the main goal of v2 verification. Resolved with PR #758 | X
462 | Hardware Loop assertion fires | RTL functional | Aug 31, 2020 | Not a bug May 17, 2022 |  | Formal check | issue from v1 that was resolved during v2 verification Hwloop constraints "solved" this issue
571 | Single stepping through hwloop does not work | RTL functional | Nov 7, 2020 | Waived June 5, 2024 |  | Simulation (directed) | single stepping over gdb, openocd, is it reproducible ? Need a test-bench with debug modules to test it.
598 | Make CSRW operations on HWLoop registers illegal and add cv.start and cv.end with register variant instruction | RTL functional | Dec 4, 2020 | Resolved Jan 26, 2023 |  | Simulation (directed) | Found by issue #189. Specification and RTL update. | X |  | X
599 | tc_clk_gating | Invalid | Dec 24, 2020 | Not a bug Jan 14, 2021 |  | Question
600 | Input address variable "raddr_a_i" in register file is 5 bit but condition is implemented on raddr_a_i[5] index? | Invalid | Jan 2, 2021 | Not a bug Jan 4, 2021 |  | Question
605 | Missing type declaration prefetch_buffer.sv | RTL coding style | Jan 20, 2021 | Resolved Apr 19, 2021 |  | Implementation | Fixed with PR #634. |  |  |  | X
606 | Clock Gating Issue for Sleep unit | Invalid | Jan 10, 2021 | Not a bug Feb 9, 2021 |  | Question
612 | some question in rtl,may be it is a bug | RTL functional |  | Not a bug June 4, 2024 |  | Inspection | still open since 01-2021, no comments, no updates cv32e40p_prefetch_controller doesn't show any incorrect behavior after a lot of non-regressions (and even a lot of test chips). It is fully covered in simulation without any waiver, this is either a performance problem not visible in simulation or not a valid assumption at all.
629 | Make illegal imm!=0 of Reg + Reg PULP instructions | RTL functional | Mar 2, 2021 | Resolved Mar 2, 2021 |  | Inspection | Resolved with PR #627 | X |  | X
650 | CV32E40P Decoder Tolerating Xpulp_NN ISA | RTL functional | Jun 28, 2021 | Resolved Aug 24, 2021 |  | Inspection | Resolved with PR #659 | X |  | X
652 | Wrong multiplication instructions' result stored in X when a preceding Zfinx instruction is executed | RTL functional | Jul 9, 2021 | Resolved Aug 30, 2023 |  | Formal Verification | Resolved with PR #860 |  | X
663 | Add more checks for illegal conditions in the PULP decoder | RTL functional | Aug 23, 2021 | Resolved Jan 5, 2022 |  | Inspection | Resolved with PR #665 | X |  | X
670 | RTL lint warnings | RTL coding style | Oct 15, 2021 | Waived June 5, 2024 |  | Lint | Not checked in v1? |  |  |  | X
684 | reg_fp* values are wrong when PULP_Zfinx is enabled | RTL functional | Mar 10, 2022 | Resolved Apr 20, 2022 |  | Inspection | Resolved with PR #685 |  |  | X
721 | OBI R-7 and R-8 violations | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | Resolved with PR #860 |  | X
722 | Wrong instruction fetch caused by multicycle F instructions ¦ Forwarding issue | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | Resolved with PR #860 |  | X
723 | Wrong data memory access of misaligned memory instructions caused by multicycle F instructions | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | Resolved with PR #860 |  | X
724 | Unknown instructions execute with no illegal instruction exception raised | RTL functional | Sep 27, 2022 | Resolved May 10, 2023 |  | Formal Verification | Resolved with PR #801 |  | X
725 | Non-Zfinx (F only) instructions execute with no illegal instruction exception raised | RTL functional | Sep 27, 2022 | Resolved May 10, 2023 |  | Formal Verification | Resolved with PR #801 |  | X
726 | F multiply accumulate instructions set underflow flag of fflags wrongly | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | cvfpu issues #94, PR #95 and #101 (release 0.8.1). T-head-Semi/opene906 issue #5 created. Resolved with PR #860 |  | X
727 | FCVT.W.S instructions set invalid operation flag of fflags wrongly | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | cvfpu issues #83, PR #97 and #101 (release 0.8.1) Resolved with PR #860 |  | X
728 | FMUL.S instructions calculate wrong result when either of the operands is 0 | RTL functional | Sep 27, 2022 | Resolved Jun 23, 2023 |  | Formal Verification | cvfpu issues #72 and PR #73 and #81 (release 0.7.0) Resolved with PR #821 |  | X
729 | FMUL.S instructions set underflow flag of fflags wrongly | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | cvfpu issues #94 and PR #98, #101 (release 0.8.1) Resolved with PR #860 |  | X
730 | Custom Xpulp instructions update register file wrongly ¦ Forwarding issue | RTL functional | Sep 27, 2022 | Resolved Aug 3, 2023 |  | Formal Verification | Resolved with PR #841 |  | X
731 | Custom Xpulp memory instructions set extra memory access | RTL functional | Sep 27, 2022 | Resolved Aug 30, 2023 |  | Formal Verification | Resolved with PR #860 |  | X
741 | Custom read-only CSRs are updated with no illegal instruction exception raised | RTL functional | Nov 28, 2022 | Resolved May 10, 2023 |  | Formal Verification | Resolved with PR #801 |  | X
742 | Custom Xpulp memory instructions update register file wrongly ¦ Simultaneous port writes | RTL functional | Nov 28, 2022 | Resolved Oct 4, 2023 |  | Formal Verification | Resolved with PR #881 |  | X
756 | Blocking assignment in an always_latch block | RTL coding style | Jan 20, 2023 | Resolved Mar 25, 2024 |  | Inspection | Manual inspection after https://github.com/openhwgroup/cv32e40p/issues/753 Resolved with PR #969 |  |  |  | X
800 | HWLoops lpstart/lpend CSRs 2 LSBs can be written to any value | RTL functional | Apr 20, 2023 | Resolved May 16, 2023 |  | Inspection | Resolved with PR #805 | X
838 | pulp hwloop count not decrementing to 0 after the end of hwloop body execution | RTL functional | Jul 25, 2023 | Resolved Aug 3, 2023 |  | Simulation (directed) | Resolved with PR #841 |  |  | X
840 | fix mimpid | RTL functional | Jul 31, 2023 | Resolved Aug 3, 2024 |  | Inspection | Resolved with PR #841 |  |  | X
850 | restrictions in HWLoop | RTL functional | Aug 11, 2023 | Resolved Aug 22, 2023 |  | Inspection | RTL alignment to User Manual, removing HWLoop hardware checks Resolved with PR #855 | X
862 | How to manage software exceptions inside HW loops? | RTL functional | Aug 31, 2023 | Resolved Sep 5, 2023 |  | Inspection | added back ecall in allowed instructions inside HWLoops in PR#865 | X
869 | data forward violation when custom xpulp instruction, cv.bsetr followed by fp instructions | RTL functional | Sep 7, 2023 | Resolved Oct 4, 2023 |  | Simulation (corev-dv) | Resolved with PR #881 |  |  | X
870 | data forward violation when custom xpulp instruction, cv.insertr followed by fp instructions | RTL functional | Sep 7, 2023 | Resolved Oct 4, 2023 |  | Simulation (corev-dv) | Resolved with PR #881 |  |  | X
876 | data forward violation when custom xpulp instruction, cv.bclrr followed by fp instructions | RTL functional | Sep 7, 2023 | Resolved Oct 4, 2023 |  | Simulation (corev-dv) | Resolved with PR #881 |  |  | X
877 | data forward violation when custom xpulp instructions, cv.extractr / cv.extractur followed by fp instructions | RTL functional | Sep 7, 2023 | Resolved Oct 4, 2023 |  | Simulation (corev-dv) | Resolved with PR #881 |  |  | X
880 | For pulp hwloops with hwloop count programmed to 0, count decrements at the end of loop to set lpcount to 0xFFFF_FFFF | RTL functional | Oct 2, 2023 | Resolved Oct 4, 2023 |  | Simulation (corev-dv) | Resolved with PR #881 |  |  | X
887 | apu_valid_i not memorized causing deadlock condition when both alu and apu write into same register at the same time | RTL functional | Oct 9, 2023 | Resolved Nov 7, 2023 |  | Simulation (corev-dv) | Resolved with PR #897 |  |  | X
888 | HWloop end CSR updated by a cancelled cv.end instruction | RTL functional | Oct 9, 2023 | Resolved Nov 7, 2023 |  | Formal Verification | Resolved with PR #897 |  | X
889 | Violation of ALU operand forwarding if preceded by FPU multicycle instruction | RTL functional | Oct 10, 2023 | Resolved Nov 7, 2023 |  | Simulation (corev-dv) | Resolved with PR #897 |  |  | X
894 | Unnecessary multiple Register File write | RTL functional | Oct 16, 2023 | Resolved Nov 9, 2023 |  | Simulation (directed) | New directed test added Resolved with PR #904 |  |  | X
896 | FLW, C_CLW, C_FLWSP instructions fail to change MSTATUS.FS to DIRTY state | RTL functional | Oct 25, 2023 | Resolved Nov 7, 2023 |  | Simulation (corev-dv) | Resolved with PR #897 |  |  | X
901 | Issue #722 correction introduced latches in combinatorial process | RTL functional | Nov 8, 2023 | Resolved Nov 9, 2023 |  | Lint | warning given by implementation tool Resolved with PR #904 |  |  |  | X
959 | Missing case default | RTL coding style | Mar 14, 2024 | Resolved Mar 14, 2024 |  | Inspection | RTL code coverage holes review Resolved with PR #961 |  |  | X
960 | Impossible to cover case default | RTL coding style | Mar 14, 2024 | Resolved Mar 14, 2024 |  | Inspection | RTL code coverage holes review Resolved with PR #961 |  |  | X
965 | FPU power consumption | RTL functional | Mar 21, 2024 | Resolved Mar 25, 2024 |  | Inspection | Resolved with PR #966 |  |  | X
975 | HWLoop count not updated when last instruction is a CSR access with pipeline flush | RTL functional | Apr 9, 2024 | Resolved Apr 9, 2024 |  | Simulation (directed) | Directed test improved after RTL code coverage holes review Resolved with PR #977 |  |  | X