## Summary_known_issue
S/N | core-v-verif ticket# | Known issue | Category | Status | Random/Custom | Example failing test(s) | Example error message(s)
1 |  | Instruction number in HWLOOP body exceeding maximum number of instruction when using immediate version of HWLOOP instructions (cv.counti, cv.setupi). This issue seen rarely, maybe 1 out of 2~3 regressions. Too risky to fix it now as it might affect other tests. | Test generation corner case | Open (no fix) | Random | corev_directed_for_hwloop_covg_test | test_program/corev_directed_for_hwloop_covg_test_550986902.S:826:(.text+0xbb4): relocation truncated to fit: R_RISCV_CVPCREL_UI12 against `hwloop1_end_stream1_id0'
2 |  | Load in Virtual Peripheral area x7 set to 0x0fffffce and going to 0x10000002 with some load address offset | Test generation corner case | Open (no fix) | Random | corev_rand_fp_instr_debug_test_with_int_debug_trigger_and_single_step | # (IDV) Instruction executed prior to mismatch '0x1a110d1e(debug_end+48): 02c3a587 flw f11,44(x7)'